## Checklist Fitur
FreshPress Laundry — Feature Checklist (Post-Merge)
# | Fitur | Kategori | Status | Keterangan | PIC
FEATURE 1 — CUSTOMER
1.1 | Homepage / Landing Page (navbar, hero, footer) | Homepage | ✅ Done |  | Person A
1.2 | Social Login (Google OAuth) | Auth | ✅ Done |  | Person A
1.3 | Register email + verifikasi + set password | Auth | ✅ Done |  | Person A
1.4 | User Login | Auth | ✅ Done |  | Person A
1.5 | Reset Password (2 halaman, sekali pakai) | Auth | ✅ Done |  | Person A
1.6 | User Profile (update data, foto upload + validasi) | Profile | ✅ Done |  | Person A
1.7 | Update email + re-verifikasi | Profile | ✅ Done |  | Person A
1.8 | Manage User Address (CRUD, set primary) | Address | ✅ Done |  | Person A
1.9 | Create Pickup Order (pilih alamat + jadwal) | Order | ✅ Done |  | Person A
1.10 | Pencarian outlet terdekat (koordinat) | Order | ✅ Done |  | Person A
1.11 | Order List & Tracking status | Order | ✅ Done |  | Person A
1.12 | Order Confirmation oleh customer | Order | ⚠️ Partial | Route backend ada, frontend belum connect ke API | Person A
1.13 | Auto-confirm 2×24 jam setelah dikirim | Order | ❌ Belum | Tidak ada cron job untuk ini | Person A
1.14 | Payment Gateway (Midtrans/Xendit) | Payment | ❌ Belum | payment.controller.ts kosong, tidak ada route | Person A
1.15 | Notifikasi otomatis jika belum bayar sampai packing | Payment | ❌ Belum | Butuh cron job + notifikasi email/socket | Person A
1.16 | Komplain order (rusak/hilang) | Complaint | ⚠️ Partial | Schema DB & UI ada, backend controller/route belum | Person A
FEATURE 2 — ADMIN / OUTLET ADMIN
2.1 | Admin Authorization (hanya admin masuk dashboard) | Auth | ✅ Done |  | Person B
2.2 | Manage User Data (CRUD outlet admin, worker, driver) | User Mgmt | ✅ Done |  | Person B
2.3 | Outlet Management (CRUD + koordinat lokasi) | Outlet Mgmt | ✅ Done |  | Person B
2.4 | Laundry Item Management (CRUD item, satuan, harga) | Outlet Mgmt | ✅ Done |  | Person B
2.5 | Clothing Type / Breakdown item pakaian | Outlet Mgmt | ✅ Done |  | Person B
2.6 | Assign Staff ke outlet (admin/worker/driver) | Outlet Mgmt | ✅ Done |  | Person B
2.7 | Show All Orders + filter outlet + role scoping | Order Mgmt | ✅ Done |  | Person B
2.8 | Create Order (input kilo + item breakdown) | Order Mgmt | ✅ Done |  | Person B
2.9 | Bypass Process (approve/reject request dari worker) | Order Mgmt | ✅ Done |  | Person B
2.10 | Sales Report (per hari/bulan/tahun, filter outlet) | Report | ✅ Done |  | Person B
2.11 | Employee Performance Report | Report | ✅ Done |  | Person B
2.12 | Attendance Report untuk outlet admin | Report | ✅ Done |  | Person B
2.13 | Work Shifts Management | Shift | ✅ Done |  | Person B
2.14 | Mobile responsive sidebar (drawer on mobile) | UI/UX | ✅ Done |  | Person B
FEATURE 3 — DRIVER & WORKER
3.1 | Attendance check-in/out + geolocation | Attendance | ✅ Done |  | Person C
3.2 | Attendance log history | Attendance | ✅ Done |  | Person C
3.3 | Driver: lihat & ambil pickup/delivery request | Driver | ✅ Done |  | Person C
3.4 | Driver: notifikasi realtime (Socket.io) | Driver | ✅ Done |  | Person C
3.5 | Driver: satu order dalam satu waktu | Driver | ✅ Done |  | Person C
3.6 | Driver: task history | Driver | ❌ Belum | Halaman ada tapi masih mock data hardcode | Person C
3.7 | Worker: lihat order per station | Worker | ✅ Done |  | Person C
3.8 | Worker: notifikasi realtime (Socket.io) | Worker | ✅ Done |  | Person C
3.9 | Worker: input ulang quantity item | Worker | ✅ Done |  | Person C
3.10 | Worker: bypass request jika quantity tidak sesuai | Worker | ✅ Done |  | Person C
3.11 | Worker: selesaikan order → lanjut station berikutnya | Worker | ✅ Done |  | Person C
3.12 | Worker packing → cek payment → status siap antar/tunggu | Worker | ✅ Done |  | Person C
3.13 | Worker: job history (riwayat pekerjaan) | Worker | ❌ Belum | Halaman /worker/history tampilkan attendance, bukan job history | Person C

## Summary
FreshPress Laundry — Progress Summary
Feature | Total Item | ✅ Done | ⚠️ Partial | ❌ Belum | Progress (%)
Feature 1 — Customer | 16 | 11 | 2 | 3 | 75
Feature 2 — Admin | 14 | 14 | 0 | 0 | 100
Feature 3 — Driver/Worker | 13 | 11 | 0 | 2 | 84.6
TOTAL | 43 | 36 | 2 | 5 | 86
❗ Prioritas Yang Harus Dikerjakan
Prioritas | Item | Feature | PIC
🔴 HIGH | Payment Gateway — controller kosong, tidak ada route | Feature 1 | Person A
🔴 HIGH | Auto-confirm 2×24 jam — butuh cron job | Feature 1 | Person A
🔴 HIGH | Notifikasi belum bayar — butuh cron job + email/socket | Feature 1 | Person A
🟡 MED | Order Confirmation frontend — connect ke API | Feature 1 | Person A
🟡 MED | Complaint API — buat controller + route backend | Feature 1 | Person A
🟡 MED | Driver task history — ganti mock data dengan real API | Feature 3 | Person C
🟡 MED | Worker job history — buat halaman riwayat pekerjaan (bukan absen) | Feature 3 | Person C